## RUMUSAN BIAYA ANGGARAN BIAYA
RUMUSAN ANGGARAN BIAYA PERSONIL
INDEKS
|  |  |  | LOKASI PROYEK : |  | JEMBER | 0.853
PELAKSANAAN OPERASIONAL PROYEK
NO | NAMA | ROLE | PENDIDIKAN | LAMA KERJA | ASAL DAERAH | INDEKS PROVINSI | LEAD PROYEK ? | MONTHLY RATE (YUMMY) | MANWEEKS RATE | MANDAYS RATE | MANHOUR RATE
1 | MOH. ARDIAS ADE AGA | PRODUCT OWNER | D4 | 2 TAHUN | JEMBER | 0.926 | 3% | 1010378.5 | 246433.7805 | 50518.925 | 8209.3253
2 | ANTON SETYO PRIHARTANTO | SOFTWARE ENGINEER | D4 | 2 TAHUN | JEMBER | 0.926 | 0% | 980950 | 239256.0976 | 49047.5 | 7970.2188
3 | RIFKY ROUDANA IMANI CAHYA | SOFTWARE ENGINEER | D4 | 2 TAHUN | JEMBER | 0.926 | 0% | 980950 | 239256.0976 | 49047.5 | 7970.2188
4 | ILMI AZMI IRADIYAH | SCRUM MASTER | D4 | 2 TAHUN | JEMBER | 0.926 | 3% | 1010378.5 | 246433.7805 | 50518.925 | 8209.3253
5 | NADEA AJENG SAFITRI | DESIGNER | D4 | 2 TAHUN | JEMBER | 0.926 | 0% | 980950 | 239256.0976 | 49047.5 | 7970.2188
[6 empty] | ORG KE 1 | ORG KE 2 | ORG KE 3 | ORG KE 4 | ORG KE 5
[5 empty] | INDEKS JEMBER | 1150000 | 1150000 | 1150000 | 1150000 | 1150000
|  |  | GAJI 1 BULAN |  | GAJI PROYEK | 980950 | 980950 | 980950 | 980950 | 980950
|  |  | ............... |  | LEAD ? | 29428.5 | 0 | 0 | 29428.5 | 0
LEAD : PRODUCT OWNER / SCRUM MASTER

## BIAYA LANGSUNG PERSONIL
BIAYA LANGSUNG PERSONIL
NO | JOB FUNCTION | JUMLAH ORANG | DURASI KERJA/ HARI (MANDAYS) | MANDAYS RATE | TOTAL BIAYA KERJA
1 | PRODUCT OWNER | 1 | 60 | 50519 | 3031140
2 | SCRUM MASTER | 1 | 60 | 50519 | 3031140
3 | DESIGNER | 1 | 60 | 49048 | 2942880
4 | SOFTWARE ENGINEER | 1 | 60 | 49048 | 2942880
5 | SOFTWARE ENGINEER | 1 | 60 | 49048 | 2942880
14890920

## PROJECT SCHEDULE MILESTONE
|  | PROJECT TITLE | SISTEM INFORMASI KASIR AKSATA FISHING SHOP
|  | PRODUCT OWNER | MOH. ARDIAS ADE AGA
|  | COMPANY NAME | GODIVA CORP
|  | TOTAL MANDAYS | 60 HARI
NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | APRIL | [19 empty] | MEI | [30 empty] | JUNI
1 | SPRINT 1 |  |  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1.1 | tampilan dashboard | 2022-04-11 | 2022-04-13 | 3 | bar: APRIL 11 to APRIL 13
1.2 | MSP - list satuan produk | 2022-04-13 | 2022-04-15 | 3 | bar: APRIL 13 to APRIL 15
1.3 | MSP - Input produk baru | 2022-04-15 | 2022-04-18 | 3 | bar: APRIL 15 to APRIL 16; APRIL 18
1.4 | MSP - edit produk | 2022-04-18 | 2022-04-20 | 3 | bar: APRIL 18 to APRIL 20
1.5 | MSP - hapus produk | 2022-04-19 | 2022-04-21 | 3 | bar: APRIL 20 to APRIL 22
1.6 | MP - list produk | 2022-04-22 | 2022-04-25 | 3 | bar: APRIL 22 to APRIL 23; APRIL 25
2 | SPRINT 2 | bar: APRIL 11 to APRIL 16; APRIL 18 to APRIL 23; APRIL 25 to APRIL 30; MEI 2 to MEI 7; MEI 9 to MEI 14; MEI 16 to MEI 21; MEI 23 to MEI 28; MEI 30 to JUNI 4; JUNI 6 to JUNI 9
2.1 | MP - cetak daftar harga | 2022-04-25 | 2022-04-27 | 3 | bar: APRIL 25 to APRIL 27
2.2 | MP - input harga + diskon | 2022-04-27 | 2022-04-29 | 3 | bar: APRIL 27 to APRIL 29
2.3 | MP - edit harga + diskon | 2022-04-29 | 2022-05-02 | 3 | bar: APRIL 29 to MEI 2
2.4 | MP - hapus harga + diskon | 2022-05-02 | 2022-05-04 | 3 | bar: MEI 2 to MEI 4
2.5 | MU - list user | 2022-05-04 | 2022-05-06 | 3 | bar: MEI 4 to MEI 6
2.6 | MU - input user | 2022-05-06 | 2022-05-09 | 3 | bar: MEI 6 to MEI 7; MEI 9
3 | SPRINT 3 | bar: APRIL 11 to APRIL 16; APRIL 18 to APRIL 23; APRIL 25 to APRIL 30; MEI 2 to MEI 7; MEI 9 to MEI 14; MEI 16 to MEI 21; MEI 23 to MEI 28; MEI 30 to JUNI 4; JUNI 6 to JUNI 9
3.1 | MU - edit user | 2022-05-09 | 2022-05-11 | 3 | bar: MEI 9 to MEI 11
3.2 | MU - hapus user | 2022-05-11 | 2022-05-13 | 3 | bar: MEI 11 to MEI 13
3.3 | ET - entry transaksi | 2022-05-13 | 2022-05-18 | 5 | bar: MEI 13 to MEI 14; MEI 16 to MEI 18
3.4 | ET - pencarian prosuk | 2022-05-18 | 2022-05-20 | 3 | bar: MEI 18 to MEI 20
3.5 | ET - konfirmasi transaksi | 2022-05-20 | 2022-05-23 | 3 | bar: MEI 20 to MEI 21; MEI 23
3.6 | MT - list transaksi harian/bulanan | 2022-05-23 | 2022-05-25 | 3 | bar: MEI 23 to MEI 25
4 | SPRINT 4 | bar: APRIL 11 to APRIL 16; APRIL 18 to APRIL 23; APRIL 25 to APRIL 30; MEI 2 to MEI 7; MEI 9 to MEI 14; MEI 16 to MEI 21; MEI 23 to MEI 28; MEI 30 to JUNI 4; JUNI 6 to JUNI 9
4.1 | MT - detail transaksi | 2022-05-25 | 2022-05-27 | 3 | bar: MEI 25 to MEI 27
4.2 | ET - cetak nota | 2022-05-27 | 2022-05-30 | 3 | bar: MEI 27 to MEI 28; MEI 30
4.3 | MT - cetak laporan | 2022-05-30 | 2022-06-01 | 3 | bar: MEI 30 to JUNI 1
4.4 | ML - login dan logout | 2022-06-01 | 2022-06-03 | 3 | bar: JUNI 1 to JUNI 3
4.5 | ML - lupa password/ganti | 2022-06-03 | 2022-06-06 | 3 | bar: JUNI 3 to JUNI 4; JUNI 6
Formulas:
START DATE = [DUE DATE, row above]

## BIAYA LANGSUNG NON-PERSONIL
BIAYA LANGSUNG NON-PERSONIL
NO | KETERANGAN | JUMLAH | UNIT | HARGA UNIT | SUB TOTAL
1 | Biaya ATK | 1 | set | 200000 | 200000
2 | Biaya Komunikasi | 3 | bulan | 40000 | 120000
3 | Alamat Website | 1 | tahun | 100000 | 100000
4 | Server | 1 | tahun | 40000 | 40000
5 | Proposal | 1 | buku | 30000 | 30000
6 | Dokumentasi Desain | 1 | buku | 30000 | 30000
7 | Dokumentasi Manual Book | 1 | buku | 30000 | 30000
8 | Nota Kesepahaman | 1 | buku | 20000 | 20000
9 | Dokumenasi Serahterima | 1 | buku | 30000 | 30000
10 | Dokumentasi Testing | 1 | buku | 30000 | 30000
11 | BIaya Pembuatan Video | 3 | video | 20000 | 60000
630000

## REKAPITULASI BIAYA PROYEK
REKAPITULASI BIAYA PROYEK
NO | KEGIATAN | SUB TOTAL
1 | BIAYA LANGSUNG PERSONIL | 14890920
2 | BIAYA LANGSUNG NON PERSONIL | 630000
SUBTOTAL |  | 15520920
3 | PPN 10% | 1552092
TOTAL |  | 17073012